## Slide 1
Month | Week | Deliverable (doc in latex) | Deliverable (doc in pptx + Jira issues) | Deliverable (Imp/tests in Ocaml/NodeJs/…)
March | W12 | Thales DIS + LSP + Related Work | Follow-up meeting | -
 | W13 | LSP + Related Work | Follow-up meeting | Set-up bitbucket repository
April | W14 | Frama-C plugin development + LSP | Follow-up meeting | Close Jira issues
 | W15 | Frama-C plugin development + Ocaml | Follow-up meeting | Close Jira issues
 | W16 | First report for the school | Follow-up meeting | Start implementation of Frama-C plug-in
 | W17 | Frama-C + C + ACSL | Follow-up meeting | Start Implementation of LSP for C/ACSL
May | W18 | Frama-C + C + ACSL | Follow-up meeting | Implement VSCode client with typescript
 | W19 | Frama-C + C + ACSL | Follow-up meeting | Initiate tests for client
 | W20 | Implementation of LSP in VSCode | Follow-up meeting | Start integration of ACSL LSP with VSCode
 | W21 | Implementation of LSP in VSCode | Follow-up meeting | First version of ACSL LSP as Frama-C Plugin
June | W22 | Inititiate section about experiments evaluation | Follow-up meeting | Close Jira issues
 | W23 | - | Follow-up meeting | Close Jira issues
 | W24 | Mid-term report for the school | Follow-up meeting | First proof of concept implementation
 | W25 | Frama-C + C + ACSL | Internal demonstration to supervisor(s) | Close Jira issues
 | W26 | Frama-C + C + ACSL | Follow-up meeting | Close Jira issues
July | W27 | Frama-C + C + ACSL | Follow-up meeting | Close Jira issues
 | W28 | Frama-C + C + ACSL | Follow-up meeting | Main syntactic features provided
 | W29 | Frama-C + C + ACSL | Follow-up meeting | Close Jira issues
 | W30 | Finalize section about VsCode, LSP, Frama-C | Follow-up meeting | Main semantic features provided
August | W31 | Finalize section about Design Choices | Follow-up meeting | Close Jira issues
 | W32 | Related works (IDEs, Common Criteria) | Follow-up meeting | Close Jira issues
 | W33 | Finalize section about experiments evaluation | Follow-up meeting | Close Jira issues
 | W34 | Summary of developpment activities/future work | Follow-up meeting | Close Jira issues
 | W35 | Final report for the school | Internal presentation to the team | Final implementation (Jira issues closed)
Project duration: 23 weeks
Follow-up meeting every week with supervisor
Open a Jira issue for each implementation task and close it as soon as the task is complete.
Deliverable versioning: put all deliverables in four separate folders (doc, meetings, src, tests). ‘tests’ are useful to benchmark the implementation progress and track regressions during development.
Maintain the latex documentation up to date every week along with the pptx presentations for follow-up meetings (keep the same material, archive latest version and highlight the newst updates every week in the same document (latex and pdf).)
Archive and update this plan if needed but anticipate risks of updates at least 2 weeks before deliverable deadlines.